## Report
2023-02-13
2023-04-09
Project Progress Report
Project Manager |  | <Fill info> |  | Receiver |  | <Fill info>
Project Name |  | <Fill info> |  | Team size |  | <Fill info>
Project Code |  | <Fill info> |  | Total estimated effort |  | 16.7375
Report Date |  | 2023-02-27 |  | Total effort spent |  | 0.125
Project Start-date |  | <Fill info> |  | Effort spent in this period |  | 0
Project End-date |  | <Fill info> |  | Total effort left |  | 16.6125
| Start |  | End |  | % Completed
Phase | Plan Start | Actual Start | Plan End | Actual End | Plan % Completed | Actual % Completed
BD | 0 | 0 | 0 | 0 | 0% | 0%
DD | 10 | 8 | 10 | 7 | 0% | 0%
PCL | 10 | 5 | 10 | 5 | 0% | 0%
Coding | 10 | 5 | 10 | 5 | 0% | 0%
UT | 6 | 2 | 5 | 0 | 0% | 0%
Details
Week | Task | PIC | Plan Start | Plan End | Actual Start | Actual End | Actual Completed
2023-02-13 | [DD]E05004 | datnt56 | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-28 | 100%
2023-02-20 | [DD]E05022 | anlvt | 2023-02-21 | 2023-02-24 | 2023-02-16 | 2023-03-13 | 100%
2023-02-27 | [DD]E05023 | anlvt | 2023-02-27 | 2023-02-28 | 2023-02-24 | 2023-03-09 | 100%
2023-02-27 | [DD]E05027 | datnt56 | 2023-03-01 | 2023-03-03 | 2023-02-27 | 2023-03-03 | 100%
2023-02-27 | [Coding]E05023 | anlvt | 2023-03-01 | 2023-03-03 | 2023-03-06 | 2023-03-06 | 100%
2023-02-27 | [PCL]E05004 | nhungpth6 | 2023-03-01 | 2023-03-03 | 2023-02-22 | 2023-02-28 | 100%
2023-02-27 | [PCL]E05005 | hoangnn20 | 2023-03-01 | 2023-03-02 | 2023-02-22 | 2023-03-02 | 100%
2023-02-27 | [PCL]E05022 | anlvt | 2023-03-01 | 2023-03-03
2023-02-27 | [PCL]E05023 | anlvt | 2023-03-01 | 2023-03-02
2023-03-06 | [DD]E05035 | datnt56 | 2023-03-06 | 2023-03-09 | 2023-03-06 | 2023-03-09 | 100%
2023-03-06 | [UT]E05023 | anlvt | 2023-03-07 | 2023-03-09
2023-03-13 | [Coding]E05005 | duyendnt | 2023-03-14 | 2023-03-16
2023-03-13 | [PCL]E05036 | nhungpth6 | 2023-03-14 | 2023-03-15 | 2023-03-14 | 2023-03-14 | 100%
2023-03-20 | [DD]E05795 | datnt56 | 2023-03-21 | 2023-03-23
2023-03-20 | [Coding]E05027 | duyendnt | 2023-03-21 | 2023-03-24 | 2023-03-01 | 2023-03-03 | 100%
2023-03-20 | [PCL]E05039 | hoangnn20 | 2023-03-21 | 2023-03-23
2023-03-27 | [Coding]E05035 | duyendnt | 2023-03-27 | 2023-03-30
Update

## WBS
|  |  |  | Plan |  |  |  | Actual |  |  |  | Status | Tool check | Note | Action
|  |  |  | Overall Plan |  | 1071.2 | 86.04% | Overall Actual |  | 398 | 91.32%
# | Phase | Task | PIC | P.Start | P.End | P.Effort | P.Completed | A.Start | A.End | A.Effort | A.Completed | Status | Tool check | Note | Action
0 | DD | [DD]E05004 | datnt56 | 2023-02-13 | 2023-02-16 | 28 | 100% | 2023-02-13 | 2023-02-28 | 50 | 100% | Completed
1 | DD | [DD]E05005 | datnt56 | 2023-02-17 | 2023-02-20 | 20 | 100% | 2023-02-21 | 2023-02-24 | 32 | 100% | Completed
2 | DD | [DD]E05022 | anlvt | 2023-02-21 | 2023-02-24 | 28 | 100% | 2023-02-16 | 2023-03-13 | 17 | 100% | Completed
3 | DD | [DD]E05023 | anlvt | 2023-02-27 | 2023-02-28 | 20 | 100% | 2023-02-24 | 2023-03-09 | 9 | 100% | Completed
4 | DD | [DD]E05027 | datnt56 | 2023-03-01 | 2023-03-03 | 28 | 100% | 2023-02-27 | 2023-03-03 | 42 | 100% | Completed
5 | DD | [DD]E05035 | datnt56 | 2023-03-06 | 2023-03-09 | 28 | 100% | 2023-03-06 | 2023-03-09 | 32 | 100% | Completed
6 | DD | [DD]E05036 | datnt56 | 2023-03-10 | 2023-03-13 | 20 | 100% | 2023-03-10 | 2023-03-13 | 24 | 100% | Completed
7 | DD | [DD]E05039 | datnt56 | 2023-03-14 | 2023-03-20 | 32 | 100% | 2023-03-14 |  | 8 | 25% | behind schedule
8 | DD | [DD]E05795 | datnt56 | 2023-03-21 | 2023-03-23 | 24 | 100% |  |  |  |  | behind schedule | warning
9 | DD | [DD]E05026 | datnt56 | 2023-03-24 | 2023-03-29 | 28 | 100% |  |  |  |  | behind schedule | warning
10 | Coding | [Coding]E05004 | duyendnt | 2023-03-01 | 2023-03-06 | 35.2 | 100% | 2023-02-27 | 2023-03-07 | 39 | 100% | Completed
11 | Coding | [Coding]E05005 | duyendnt | 2023-03-14 | 2023-03-16 | 25.6 | 100% |  |  |  |  | behind schedule | warning
12 | Coding | [Coding]E05022 | anlvt | 2023-03-01 | 2023-03-06 | 35.2 | 100% | 2023-03-07 | 2023-03-10 | 10 | 100% | Completed
13 | Coding | [Coding]E05023 | anlvt | 2023-03-01 | 2023-03-03 | 25.6 | 100% | 2023-03-06 | 2023-03-06 | 8 | 100% | Completed
14 | Coding | [Coding]E05027 | duyendnt | 2023-03-21 | 2023-03-24 | 35.2 | 100% | 2023-03-01 | 2023-03-03 | 12 | 100% | Completed
15 | Coding | [Coding]E05035 | duyendnt | 2023-03-27 | 2023-03-30 | 35.2 | 100% |  |  |  |  | behind schedule | warning
16 | Coding | [Coding]E05036 | datnt56 | 2023-03-30 | 2023-04-03 | 25.6 | 100% |  |  |  |  | behind schedule | warning
17 | Coding | [Coding]E05039 | duyendnt | 2023-03-31 | 2023-04-06 | 44.8 | 100% |  |  |  |  | behind schedule | warning
18 | Coding | [Coding]E05795 | datnt56 | 2023-04-04 | 2023-04-07 | 32 | 100% |  |  |  |  | behind schedule | warning
19 | Coding | [Coding]E05026 | duyendnt | 2023-04-07 | 2023-04-12 | 35.2 | 25% |  |  |  |  | behind schedule | warning
20 | PCL | [PCL]E05004 | nhungpth6 | 2023-03-01 | 2023-03-03 | 16 | 100% | 2023-02-22 | 2023-02-28 | 18 | 100% | Completed
21 | PCL | [PCL]E05005 | hoangnn20 | 2023-03-01 | 2023-03-02 | 12 | 100% | 2023-02-22 | 2023-03-02 | 19 | 100% | Completed
22 | PCL | [PCL]E05022 | anlvt | 2023-03-01 | 2023-03-03 | 16 | 100% |  |  |  |  | behind schedule | warning
23 | PCL | [PCL]E05023 | anlvt | 2023-03-01 | 2023-03-02 | 12 | 100% |  |  |  |  | behind schedule | warning
24 | PCL | [PCL]E05027 | nhungpth6 | 2023-03-09 | 2023-03-13 | 16 | 100% | 2023-03-09 | 2023-03-13 | 14 | 100% | Completed
25 | PCL | [PCL]E05035 | hoangnn20 | 2023-03-10 | 2023-03-14 | 16 | 100% | 2023-03-09 | 2023-03-14 | 14 | 100% | Completed
26 | PCL | [PCL]E05036 | nhungpth6 | 2023-03-14 | 2023-03-15 | 12 | 100% | 2023-03-14 | 2023-03-14 | 5 | 100% | Completed
27 | PCL | [PCL]E05039 | hoangnn20 | 2023-03-21 | 2023-03-23 | 24 | 100% |  |  |  |  | behind schedule | warning
28 | PCL | [PCL]E05795 | nhungpth6 | 2023-03-24 | 2023-03-28 | 16 | 100% |  |  |  |  | behind schedule | warning
29 | PCL | [PCL]E05026 | hoangnn20 | 2023-03-31 | 2023-04-04 | 16 | 100% |  |  |  |  | behind schedule | warning
30 | UT | [UT]E05004 | duyendnt | 2023-03-07 | 2023-03-13 | 35.2 | 100% | 2023-03-08 |  | 43 | 90% | behind schedule
31 | UT | [UT]E05005 | hoangnn20 | 2023-03-24 | 2023-03-28 | 25.6 | 100% |  |  |  |  | behind schedule | warning
32 | UT | [UT]E05022 | anlvt | 2023-03-07 | 2023-03-13 | 35.2 | 100% | 2023-03-08 |  | 2 | 20% | behind schedule
33 | UT | [UT]E05023 | anlvt | 2023-03-07 | 2023-03-09 | 25.6 | 100% |  |  |  |  | behind schedule | warning
34 | UT | [UT]E05027 | nhungpth6 | 2023-04-12 | 2023-04-18 | 35.2 | 0% | [5 empty] | warning
35 | UT | [UT]E05035 | nhungpth6 | 2023-03-31 | 2023-04-06 | 35.2 | 100% |  |  |  |  | behind schedule | warning
36 | UT | [UT]E05036 | nhungpth6 | 2023-04-19 | 2023-04-21 | 25.6 | 0% | [5 empty] | warning
37 | UT | [UT]E05039 | hoangnn20 | 2023-04-07 | 2023-04-14 | 44.8 | 16.67% |  |  |  |  | behind schedule | warning
38 | UT | [UT]E05795 | datnt56 | 2023-04-10 | 2023-04-14 | 32 | 0% | [5 empty] | warning
39 | UT | [UT]E05026 | hoangnn20 | 2023-04-17 | 2023-04-21 | 35.2 | 0% | [5 empty] | warning

## Gantt
[DD]E05004 | 2023-02-13 | 2023-02-16
[DD]E05005 | 2023-02-17 | 2023-02-20
[DD]E05022 | 2023-02-21 | 2023-02-24
[DD]E05023 | 2023-02-27 | 2023-02-28
[DD]E05027 | 2023-03-01 | 2023-03-03
[DD]E05035 | 2023-03-06 | 2023-03-09
[DD]E05036 | 2023-03-10 | 2023-03-13
[DD]E05039 | 2023-03-14 | 2023-03-20
[DD]E05795 | 2023-03-21 | 2023-03-23
[DD]E05026 | 2023-03-24 | 2023-03-29

## Workload
start | anlvt | datnt56 | duyendnt | hoangnn20 | nhungpth6
2023-02-13 |  | 8
2023-02-14 |  | 8
2023-02-15 |  | 8
2023-02-16 |  | 8
2023-02-17 |  | 8
2023-02-18 |  | 8
2023-02-19 |  | 8
2023-02-20 |  | 8
2023-02-21 | 8
2023-02-22 | 8
2023-02-23 | 8
2023-02-24 | 8
2023-02-27 | 8
2023-02-28 | 8 |  |  |  |  | np
2023-03-01 | 32 | 8 | 8 | 8 | 8
2023-03-02 | 32 | 8 | 8 | 8 | 8
2023-03-03 | 24 | 8 | 8 |  | 8
2023-03-04 | 8 |  | 8
2023-03-05 | 8 |  | 8
2023-03-06 | 8 | 8 | 8
2023-03-07 | 16 | 8 | 8
2023-03-08 | 16 | 8 | 8
2023-03-09 | 16 | 8 | 8 |  | 8
2023-03-10 | 8 | 8 | 8 | 8 | 8
2023-03-11 | 8 | 8 | 8 | 8 | 8
2023-03-12 | 8 | 8 | 8 | 8 | 8
2023-03-13 | 8 | 8 | 8 | 8 | 8
2023-03-14 |  | 8 | 8 | 8 | 8
2023-03-15 |  | 8 | 8 |  | 8
2023-03-16 |  | 8 | 8
2023-03-17 |  | 8
2023-03-18 |  | 8
2023-03-19 |  | 8
2023-03-20 |  | 8
2023-03-21 |  | 8 | 8 | 8
2023-03-22 |  | 8 | 8 | 8
2023-03-23 |  | 8 | 8 | 8
2023-03-24 |  | 8 | 8 | 8 | 8
2023-03-25 |  | 8 |  | 8 | 8
2023-03-26 |  | 8 |  | 8 | 8
2023-03-27 |  | 8 | 8 | 8 | 8
2023-03-28 |  | 8 | 8 | 8 | 8
2023-03-29 |  | 8 | 8
2023-03-30 |  | 8 | 8
2023-03-31 |  | 8 | 8 | 8 | 8
2023-04-01 |  | 8 | 8 | 8 | 8
2023-04-02 |  | 8 | 8 | 8 | 8
2023-04-03 |  | 8 | 8 | 8 | 8
2023-04-04 |  | 8 | 8 | 8 | 8
2023-04-05 |  | 8 | 8 |  | 8
2023-04-06 |  | 8 | 8 |  | 8
2023-04-07 |  | 8 | 8 | 8
2023-04-08 |  |  | 8 | 8
2023-04-09 |  |  | 8 | 8
2023-04-10 |  | 8 | 8 | 8
2023-04-11 |  | 8 | 8 | 8
2023-04-12 |  | 8 | 8 | 8 | 8
2023-04-13 |  | 8 |  | 8 | 8
2023-04-14 |  | 8 |  | 8 | 8
2023-04-15 |  |  |  |  | 8
2023-04-16 |  |  |  |  | 8
2023-04-17 |  |  |  | 8 | 8
2023-04-18 |  |  |  | 8 | 8
2023-04-19 |  |  |  | 8 | 8
2023-04-20 |  |  |  | 8 | 8
2023-04-21 |  |  |  | 8 | 8
Update

## EVM
From: | 2023-02-13
To: | 2023-04-10
Week | PV | EV | AC | SPI | CPI
2023-02-13 | 48 | 48 | 82 | 1 | 0.58537
2023-02-20 | 96 | 7968 | 97 | 83 | 82.1443
2023-02-27 | 344 | 61920 | 8161 | 180 | 7.5873
2023-03-06 | 734.4 | 6125547.78 | 70114 | 8340.8875 | 87.3655
2023-03-13 | 1414.4 | 110966418.6057 | 6195593.78 | 78454.7643 | 17.9105
2023-03-20 | 2821.6 | 17702854979.548 | 117161922.3857 | 6274048.405 | 151.0973
2023-03-27 | 5684.8 |  | 17820016881.9337
2023-04-03 | 11376.8 |  | 17820016881.9337
EVM Report

## Effort
PIC | Effort
FPT-1 | 32
FPT-2 | 41.2
FPT-3 | 19.5
FPT-4 | 41.2

## Timesheet
Date | PIC | Task | TOW | Hours | % completed | Description
Hello World | LongPH5 | Task-01 | Create | 8 | 100% | Test
2024-03-19 | LongPH5 | Task-01 | Create | 8 | 100% | Test
2024-03-19 | LongPH5 | Task-01 | Create | 8 | 100% | Test
2024-03-19 | LongPH5 | Task-01 | Create | 8 | 100% | Test
2024-03-19 | LongPH5 | Task-01 | Create | 8 | 100%
2024-03-19 | LongPH5 | Task-01 | Create | 8 | 100%
2024-03-19 | LongPH5 | Task-01 | Create | 8 | 100% | abc
2024-03-19 | LongPH5 | Task-01 | Create | 8 | 100% | abc

## holidays
# | Date | Note
1 | 2023-01-01 | New Year's Day
2 | 2023-01-02 | Compensatory day-off for New Year's Day
3 | 2023-01-20 | Lunar New Year Festival
4 | 2023-01-23 | Lunar New Year Festival
5 | 2023-01-24 | Lunar New Year Festival
6 | 2023-01-25 | Lunar New Year Festival
7 | 2023-01-26 | Lunar New Year Festival
8 | 2023-04-29 | Hung Kings Anniversary Day
9 | 2023-04-30 | Liberation Day
10 | 2023-05-01 | International Labor Day
11 | 2023-05-02 | Compensatory day-off for Hung Kings Anniversary Day and Liberation Day
12 | 2023-05-03 | Compensatory day-off for Hung Kings Anniversary Day and Liberation Day
13 | 2023-09-01 | National Day
14 | 2023-09-04 | National Day